CultOps Go-Live Plan

Version 3.2 — Corrected Architecture & Migration Strategy (Soft-Reset with Order/Product Preservation)

Target: Monday, March 3, 2026

Prepared: March 1, 2026

⚠ CRITICAL UPDATE: This plan supersedes v1 and v2. Previous versions assumed empty databases. Investigation revealed the live app uses a Bolt.new-provisioned Supabase instance with existing data.

# 1. Architecture Discovery

During preparation for go-live, a critical architecture finding was uncovered: the CultOps application running on Bolt.new does NOT use the Supabase projects visible in the user's Supabase dashboard. Instead, Bolt.new provisions its own Supabase instance behind the scenes.

## 1.1 Three Supabase Instances

| Instance | Project Ref | Status | Tables |
| --- | --- | --- | --- |
| cult-ops (Dashboard) | fhjcvdimdgzwrijotmxg | EMPTY | 0 |
| cult-ops-dev (Dashboard) | uayyhluztelnfxfvdhyt | EMPTY | 0 |
| Bolt.new Instance (LIVE) | fonreynkfeqywshijqpi | ACTIVE | 40+ |

ℹ The Bolt.new instance (fonreynkfeqywshijqpi) is the ONLY instance with data and schema. All go-live operations must target this instance.

# 2. Live Database State (as of Feb 28, 2026)

Direct REST API queries against the Bolt.new Supabase instance revealed the following data state:

## 2.1 Row Counts

| Table | Rows | Notes |
| --- | --- | --- |
| batch_registry | 62 | Most in pre_harvest or created state |
| certificates_of_analysis | 0 | NO COAs uploaded yet |
| inventory_items | 121 | Packaged items, test_mode: false |
| strains | 43 | Populated by app. RESTRICT FKs from order_items & products block DELETE. |
| order_items | 498 | REAL DATA — RESTRICT FK to strains. Must SET NULL before strain DELETE. |
| products | 1,026 | REAL DATA — RESTRICT FK to strains. Must SET NULL before strain DELETE. |
| internal_bucked_inventory | 74 | Test data — RESTRICT FK to strains. Safe to DELETE. |
| internal_bulk_inventory | 100 | Test data — RESTRICT FK to strains. Safe to DELETE. |

## 2.2 Critical Finding: RESTRICT FK Constraints Block Strain Deletion

⚠ The strains table now has 43 rows (populated by the app), but four tables hold RESTRICT foreign keys to strains.id. A plain DELETE FROM strains will fail until every child row is removed or its strain_id is SET NULL. Two of these tables—order_items (498 rows) and products (1,026 rows)—contain REAL production data that must be preserved.

Tables with RESTRICT foreign keys to strains.id:

| Table | Rows | Data Type | Reset Strategy |
| --- | --- | --- | --- |
| order_items | 498 | REAL DATA | SET NULL strain_id before DELETE strains, then re-link after new strains inserted |
| products | 1,026 | REAL DATA | SET NULL strain_id before DELETE strains, then re-link after new strains inserted |
| internal_bucked_inventory | 74 | Test data | DELETE rows before DELETE strains |
| internal_bulk_inventory | 100 | Test data | DELETE rows before DELETE strains |

Impact: The reset must use a soft-reset strategy: (1) SET NULL on strain_id in order_items and products to detach real data from old strain UUIDs, (2) DELETE test-data tables and strains, (3) upload fresh strains from audit data, (4) re-link order_items and products to new strain UUIDs by matching on strain name. See Section 4.2 for the full sequence.

## 2.3 Batch Lifecycle States Observed

Sample of 10 most recent batches from the live database:

| Batch # | Strain | Harvest | Status | Lifecycle | Has COA |
| --- | --- | --- | --- | --- | --- |
| 260225-DON | Donny Burger | — | active | pre_harvest | No |
| 260220-DIF | Dante's Inferno | 2026-02-20 | active | created | No |
| 260220-STP | Stay Puft | 2026-02-20 | active | created | No |
| 260105-DIF | Dante's Inferno | — | active | pre_harvest | No |
| 260112-CHL | Chemlatto | — | active | pre_harvest | No |
| 260202-STP | Stay Puft | — | active | pre_harvest | No |
| 260207-THL | Tahoe Larry | — | active | pre_harvest | No |
| 260211-ZCH | Z Chem | — | active | pre_harvest | No |

## 2.4 Inventory Items Sample

121 inventory items exist. Sample records show packaged products with production data (test_mode: false):

260227-BLM-001 | Packaged – Black Maple – 14g Smalls | qty:26 | Available

260217-MGM-003 | Packaged – Magic Marker – 3.5g Flower | qty:57 | Available

# 3. Corrected Schema Reference

The following schema is extracted directly from the live database.types.ts file (229,496 chars) in the Bolt.new codebase. Previous plan versions had incorrect column name assumptions.

## 3.1 Schema Corrections vs. Previous Plans

| Table | Assumed (v1/v2) | Actual (Live) | Impact |
| --- | --- | --- | --- |
| batch_registry | batch_id (column) | batch_number | All SQL must use batch_number |
| batch_registry | strain_name | strain | Column name is just 'strain' |
| certificates_of_analysis | — | strain_name | COA table DOES use strain_name |
| inventory_items | batch_id nullable | batch_id REQUIRED | Every item MUST link to a batch |
| inventory_items | — | test_mode REQUIRED | Must set to false for production |
| inventory_items | — | reserved_qty NOT NULL | Defaults to 0, must provide |
| strains | name only | name + display_name | Both fields are REQUIRED |
| strains | — | is_active REQUIRED | Boolean, cannot be null |

## 3.2 Upload Order (Respecting Foreign Keys)

Tables must be populated in this exact sequence due to foreign key constraints:

- strains — No FK dependencies. Must populate first so batch_registry.strain_id has valid targets.

- batch_registry — FK to strains.id (strain_id). Leave coa_id null initially.

- certificates_of_analysis — FK to batch_registry.id (batch_id). Upload COA data + PDF files.

- UPDATE batch_registry.coa_id — Backfill the bidirectional link from batch to COA.

- inventory_items — FK to batch_registry.id (batch_id), strains.id (strain_id).

# 4. Migration Strategy: Full Reset

Per project requirements, a FULL RESET of inventory data is needed. This means deleting all existing records and uploading fresh data from the audit spreadsheet and COA lab results.

## 4.1 Why Full Reset

- Existing 62 batches were created during development/testing and may have inconsistent data

- Strains table is empty with orphaned references — needs clean population

- Zero COAs uploaded — fresh upload required regardless

- 121 inventory items need reconciliation with current physical inventory counts

- Clean slate ensures data integrity for production go-live

## 4.2 Soft-Reset Sequence (Preserve Orders & Products)

⚠ SOFT RESET — order_items (498 rows) and products (1,026 rows) contain REAL production data. Their strain_id FKs must be SET NULL before strains can be deleted, then re-linked after new strains are uploaded (see Section 4.2.1).

Phase A — Detach real data from old strain UUIDs

- UPDATE order_items SET strain_id = NULL WHERE strain_id IS NOT NULL

- UPDATE products SET strain_id = NULL WHERE strain_id IS NOT NULL

Phase B — FK-ordered DELETE of inventory, test, and cultivation tables

- DELETE FROM package_assignments (FK to order_items, package_ids)

- DELETE FROM inventory_audit_lines (FK to inventory_items — SET NULL)

- DELETE FROM variance_log (FK to inventory_items, inventory_movements)

- DELETE FROM inventory_movements (FK to inventory_items via source/dest)

- DELETE FROM labels (references package_id by text — dangling refs)

- DELETE FROM inventory_items

- DELETE FROM conversion_packages (RESTRICT FK to batch_registry)

- DELETE FROM conversion_variance_log (RESTRICT FK to batch_registry)

- DELETE FROM trim_sessions (FK to batch_registry — SET NULL)

- DELETE FROM packaging_sessions (FK to batch_registry — SET NULL)

- DELETE FROM bucking_sessions (FK to batch_registry — SET NULL)

- DELETE FROM internal_bucked_inventory (RESTRICT FK to strains — test data, 74 rows)

- DELETE FROM internal_bulk_inventory (RESTRICT FK to strains — test data, 100 rows)

- DELETE FROM certificates_of_analysis

- DELETE FROM batch_registry

Phase C — Delete strains (now safe after SET NULL and child DELETEs)

- DELETE FROM strains

Note: Phase A SET NULL ensures order_items and products survive the strain wipe. After fresh strains are uploaded (Phase 2 of Go-Live), run the re-link queries in Section 4.2.1 to restore strain_id references using strain name matching. Wrap each phase in BEGIN / COMMIT for atomicity.

### 4.2.1 Post-Reset Re-Link Strategy

After Phase 2 (Strain Upload) inserts fresh strain records, the orphaned strain_id columns in order_items and products must be restored. Run these UPDATE queries to re-link by matching on the strain name stored in each table:

Re-link order_items:

UPDATE order_items oi SET strain_id = s.id FROM strains s WHERE oi.strain = s.name AND oi.strain_id IS NULL;

Re-link products:

UPDATE products p SET strain_id = s.id FROM strains s WHERE p.strain_name = s.name AND p.strain_id IS NULL;

⚡ VERIFY: After re-link, confirm zero NULLs remain: SELECT COUNT(*) FROM order_items WHERE strain_id IS NULL; SELECT COUNT(*) FROM products WHERE strain_id IS NULL; — If any remain, the strain name in that row does not match any name in the strains table (check for typos or aliases).

## 4.3 Upload Method

Since the live Supabase instance is only accessible through the Bolt.new environment, the upload path uses Node.js scripts running in the Bolt.new WebContainer terminal.

### Method: Supabase JS Client (Primary)

The CultOps project already has @supabase/supabase-js installed. Migration scripts will import it directly:

// migrate.mjs — Run in Bolt.new Terminal

import { createClient } from '@supabase/supabase-js';

const sb = createClient(

'https://fonreynkfeqywshijqpi.supabase.co',

process.env.VITE_SUPABASE_ANON_KEY

);

### Method: REST API Fallback

If the JS client approach fails, direct REST API calls via Node https module:

POST /rest/v1/strains  (with JSON body)

POST /rest/v1/batch_registry  (with JSON body)

Headers: apikey + Authorization: Bearer <anon_key>

### Method: Supabase SQL Editor (if accessible)

If the Bolt.new Supabase project is accessible via the Supabase Dashboard at supabase.com/dashboard/project/fonreynkfeqywshijqpi, raw SQL can be executed in the SQL Editor. This is the most reliable method for bulk operations.

# 5. Data Preparation

## 5.1 Source Data Summary

| Source | Records | Contents |
| --- | --- | --- |
| Audit Spreadsheet | 131 Binned | Physical inventory counts by batch/strain |
| Audit Spreadsheet | 5 Bucked | Bucked flower weights |
| Audit Spreadsheet | 34 Batches | Batch registry with harvest dates, rooms, weights |
| COA Lab CSV | 51 tests / 42 batches | THC%, CBD%, terpene profiles, lab results |

## 5.2 Strain Master List

Strains must be populated first. The following strains are referenced across the audit data and live database. Each needs a UUID, name, display_name, abbreviation, and is_active = true.

Strain corrections applied: Flava Flav → Flavor Flav, Super Silver Marker → Silver Marker

## 5.3 COA Handling

- COA lab data comes from the CSV with 51 test records across 42 unique batch IDs

- Where two COAs exist for the same batch, use the one with higher THC percentage

- Total THC = D9-THC + (THCA × 0.877)

- COA PDF files must be uploaded to Supabase Storage manually via the CultOps UI (Justin to do)

- The pdf_file_path column stores the Supabase Storage path after upload

## 5.4 Batch Number Encoding

Batch numbers follow the format YYMMDD-XXX where XXX is a 3-letter uppercase strain abbreviation. All 34 batches in the current audit use exactly 3 letters. The database CHECK constraint enforces this pattern.

251121-MGM  =  Nov 21, 2025 — Magic Marker

260220-DIF  =  Feb 20, 2026 — Dante's Inferno

260227-BLM  =  Feb 27, 2026 — Black Maple

# 6. Go-Live Execution Plan

The following checklist outlines every step for Monday, March 3, 2026.

## Phase 0: Pre-Flight (Sunday Evening)

- Verify Bolt.new terminal access is working

- Confirm audit spreadsheet data is finalized

- Prepare all migration scripts locally (JSON data files + upload scripts)

- Test a single strain INSERT to verify API connectivity

## Phase 1: Database Soft-Reset (Monday AM)

⚡ BACKUP: Before deleting any data, export current state via REST API queries to local JSON files. Wrap the entire reset in a SQL transaction (BEGIN / COMMIT) so any failure rolls back cleanly.

- Phase A — Detach real data: UPDATE order_items SET strain_id = NULL; UPDATE products SET strain_id = NULL; (see Section 4.2 Phase A)

- Phase B — FK-ordered DELETE: Delete 15 dependent and core tables in FK order (see Section 4.2 Phase B for full sequence)

- Phase C — Delete strains: DELETE FROM strains (now safe after SET NULL and child DELETEs)

- Verify all core tables show 0 rows via count queries; confirm order_items and products still have their original row counts (498 / 1,026) with strain_id = NULL

## Phase 2: Strain Upload

- Generate strain JSON from audit data (name, display_name, abbreviation, is_active: true)

- POST to /rest/v1/strains or use Supabase JS client .insert()

- Verify row count matches expected strain count

- Record all strain UUIDs for FK references in subsequent uploads

## Phase 3: Batch Upload

- Generate batch JSON from audit spreadsheet (34 batches) + any additional live batches

- Map each batch to its strain_id UUID from Phase 2

- Set lifecycle_state based on current status (e.g., pre_harvest, created, bulk_available, packaged)

- POST to /rest/v1/batch_registry

- Verify 34+ batches created, record all batch UUIDs

## Phase 4: COA Upload

- Generate COA JSON from lab CSV (42 unique batches, highest-THC record per batch)

- Map each COA to its batch_id UUID from Phase 3

- POST to /rest/v1/certificates_of_analysis

- Run UPDATE on batch_registry to set coa_id (bidirectional link)

- Justin: Upload COA PDFs via CultOps UI to Supabase Storage

## Phase 5: Inventory Upload

- Generate inventory JSON from audit data (Binned + Bucked + Packaged items)

- Map each item to batch_id and strain_id from previous phases

- Set required fields: test_mode: false, reserved_qty: 0, on_hand_qty: (must equal available_qty when reserved_qty is 0 — ATP CHECK constraint: available_qty = on_hand_qty − COALESCE(reserved_qty, 0))

- Generate package_id values in format YYMMDD-CODE-NNN

- TRIGGER MITIGATION: The inventory_items table has BEFORE/AFTER INSERT triggers that auto-register batches and populate batch_number/strain_id. To avoid conflicts, provide batch_id UUID directly in each INSERT (not batch_number). Verify trigger behaviour in Bolt.new terminal with a single test row before bulk insert.

- POST to /rest/v1/inventory_items

- Verify counts match audit: 131 Binned + 5 Bucked + Packaged items

## Phase 6: Verification

- Query all 4 core tables for row counts

- Spot-check 5-10 records per table for data accuracy

- Open CultOps app and verify dashboard shows correct totals

- Test batch detail view — confirm COA links work

- Test inventory list — confirm quantities match audit

- Test strain filter — confirm all strains appear

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Bolt.new terminal fails | Medium | High | Fallback: Use Supabase Dashboard SQL Editor if accessible, or browser console REST API calls |
| RLS policies block inserts | Medium | High | Use service_role key (find in Bolt.new .env or Supabase settings) instead of anon key |
| FK constraint violations | Low | High | Strict upload order (strains → batches → COAs → inventory). Validate IDs before INSERT. |
| Orphaned data in related tables | Medium | Medium | Check packaging_sessions, trim_sessions for FK refs before deleting batches |
| Bolt.new token limit reached | Already occurred | Low | Terminal still works despite token exhaustion. Only Bolt AI is affected. |
| App shows stale cached data | Low | Low | Hard refresh (Ctrl+Shift+R) or clear Supabase client cache |
| COA PDF upload fails | Low | Medium | Manual upload via Supabase Storage dashboard as fallback |

# 8. Quick Environment Reference

Live Supabase URL: https://fonreynkfeqywshijqpi.supabase.co

Bolt.new Project: https://bolt.new/~/sb1-e6rq2s5m

Anon Key: eyJhbG...VejHxwGKbc (stored in .env as VITE_SUPABASE_ANON_KEY)

Schema Types File: src/lib/database/database.types.ts (229,496 chars)

## Core Table Column Quick-Reference

batch_registry: id, batch_number, strain, harvest_date, room, initial_weight_grams, coa_id, status, lifecycle_state, strain_id, is_quarantined, notes

certificates_of_analysis: id, strain_name, batch_number, thc_percentage, cbd_percentage, total_cannabinoids_percentage, total_terpenes_mg_g, terpene_1_name/value/percentage (x3), pdf_file_path, batch_id

inventory_items: id, package_id (REQUIRED), product_name, batch, strain, status, category, available_qty, net_weight, unit, batch_number, batch_id (REQUIRED), test_mode (REQUIRED: false), reserved_qty (REQUIRED: 0), strain_id

strains: id, name (REQUIRED), display_name (REQUIRED), abbreviation, dominance_type, is_active (REQUIRED: true), category

End of Document — CultOps Go-Live Plan v3.1 (Updated March 1, 2026 — FK cleanup sequence expanded per Bolt.new schema analysis)